## Masterarbeit Enno
| Titel: | MetaProt_STAT | Estimated Time
| GOAL (SMART) | Development of a pipeline for data evaluation, machine learning and visualization for metaproteome data
| Milestone 1 | Incoorporate in R Create WIKI Create GIT Repository Create a concept for teaching Create timeline for project management | 2020-04-08
| Milestone 2 | R-Script + Docu for Normalization R-Script + Docu for Group Comparison of variables within 2 groups (T-test, Mann-Whitney U-Test) R-Script + Docu for Group Comparison of 2 groups (ANOSIM, PERMANOVA) R-Script + Docu for comparison of multiple groups (ANOVA, Kruskal-Wallis-Test) --> give a training session for Students | 2020-04-22 | Wiki: intro to R etc, develop R script, shiny 7 dashboard, intro to those tests, outputs
| Milestone 3 | R-Script + Docu for Clustering and clustered heatmap R-Script + Docu for PCA, PcOA and NMDS + CCA --> give a training session for students | 2020-05-06
| Milestone 4 | Add scripts and docu for Krona and Chord | 2020-05-27
R-Script + Docu for violine plots
Add two more fancy visualizations
| Milestone 5 | Develop a concept for machine learning | 2020-06-27
Prepare R-scripts and docu for machine learning --> give a training session for students
| Milestone 6 | Develop own Milestone to improve statistics and visualization | 2020-07-27
|  | GANTT Diagramm | Arbeitsaufwand |  | Vorarbeiten | 1. Monat |  |  |  | 2. Monat |  |  |  | 3. Monat |  |  |  | 4. Monat |  |  |  | 5. Monat |  |  |  | 6. Monat
|  | Arbeitspakete | Dauer (geschätzt) | Dauer (real) |  | 1. WO | 2. WO | 3. WO | 4. WO | 5. WO | 6. WO | 7. WO | 8. WO | 9. WO | 10. WO | 11. WO | 12. WO | 13. WO | 14. WO | 15. WO | 16. WO | 17. WO | 18. WO | 19. WO | 20. WO | 21. WO | 22. WO | 23. WO | 24. WO
|  | A1. Einschleusung, Einführung Vortrag, Sicherheitsbelehrung | 1
|  | A2. Methode teaching | 2
|  | A3. Proteinextraction, Amidoblack, SDS-PAGE, FASP, LC-MS/MS Measurement | 6
|  | A4. Selection of database for protein ID | 1
|  | A5. Xtandem, OMSSA, MASCOT und BLAST Suche und export Ergebnismatrix | 2
|  | A6. Beschreibung des durchschnittlichen Darmmikrobiomes | 3
|  | A7. Beschreibung der Änderungen während der Therapie | 3
|  | A6. Abgeschlossene Statistische Tests (Normalisierung T-Test, Clustering, PCA) für Metaproteine, biol. Processe, Ordnungen | 2
GANTT- Legende
geplant |  | A7. Schreiben der eigenen Arbeit | 4
abgeschlossen |  | Summe | 24
| Weekly Meeting | Description | Result
Datum
| 2020-04-01 | Kick-OFF,

## Take Home Projektmanagement
Projektmanagement Take Home
1.) Kommunikationskultur bestend aus konkreter Verantwortung und Kommunikation von Problemen
2.) klar definiertes Ziel als Zustand (spezifisch, messbar, erreichbar, realistisch, terminiert)
3.) Störungsfreie Arbeitszeit
4.) realistische Arbeitszeiten, 220 Tage pro Jahr; 18,3 Tage pro Monat und 70% wirklich auf Projektbezogen
5.) Projektmanagement mit einplanen
6.) Planung GANTT Chart kritischer Pfad,
7.) Reserven einplanen aber erst nach Arbeitspaketen (Faktor: 1,2 Normal; 1,4 Technologieorientiert; 1,6 Grenzanforderung; 2,0 Grundlagenforschung+10-20% Projektmanagement)
8.) Blindleistung vermeiden, parallele Projektberarbeitung, langes Suchen,
9.) Projekt und Dokumentationskultur